## Draft WP
BIOMASS RENEWABLE / BIOMASS ENERGY OPERATING CONTRACT (BREOC/BEOC)
Project Name
Project Location
WORK PROGRAM
ACTIVITIES | Year 1 (2027) |  |  |  |  | Year 2 (2028) |  |  |  | Year 3 (2029) |  |  |  | Year 4 (2030) |  |  |  | Financial Commitment (Php)
| 1 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | Y1 | Y2 | Y3 | Y4
A IN-HOUSE ACTIVITIES
1 Project Development/Management | bar: Year 1 (2027) 1 to Year 4 (2030) 3
2 Secure Valid Feedstock Supply Agreements | bar: Year 1 (2027) 1 to Year 1 (2027) 3
3 Financial Closing | bar: Year 1 (2027) 1 to Year 1 (2027) 3
4. Approval / Signing of EPC Contract | bar: Year 1 (2027) 1 to Year 1 (2027) 4
5. Licensing / Permits / Clearances
a. NCIP (Certificate of No Objection) | bar: Year 1 (2027) 1 to Year 1 (2027) 4
b. NWRB | bar: Year 1 (2027) 1 to Year 1 (2027) 4
c. LGU Resolution of Support | bar: Year 1 (2027) 1 to Year 1 (2027) 4
d.Business Permit | bar: Year 1 (2027) 1 to Year 1 (2027) 4
6 Interconnection Permits / Licences / Clearances
a. System / Distribution Impact Study | bar: Year 1 (2027) 1 to Year 1 (2027) 3
b. Facility Study | bar: Year 1 (2027) 3 to Year 1 (2027) 4
7. DENR-EMB (Environmental Compliance Certificate) | bar: Year 1 (2027) 1 to Year 1 (2027) 4
B ENGINEERING, PROCUREMENT & CONSTRUCTION (EPC)
1 Detailed Engineering Work | bar: Year 2 (2028) 1 to Year 3 (2029) 2
2 Procurement and Manufacturing | bar: Year 2 (2028) 2 to Year 3 (2029) 3
3 Civil Works | bar: Year 2 (2028) 2 to Year 4 (2030) 2
4 Mechanical Installation Work | bar: Year 2 (2028) 2 to Year 4 (2030) 2
5 Electrical and Control System | bar: Year 2 (2028) 2 to Year 4 (2030) 2
C. TESTING AND COMMISSIONING
1. Pre-Commissioning / Internal Testing | bar: Year 4 (2030) 1 to Year 4 (2030) 2
2. NGCP/DU Commissioning | bar: Year 4 (2030) 2 to Year 4 (2030) 3
D. PRE-COMMERCIAL OPERATION REQUIREMENTS
1.IEMOP/WESM Registration | bar: Year 4 (2030) 3
2. Connection/Transmission/Metering Service Agreements | bar: Year 4 (2030) 3
3.ERC (Certificate of Compliance / Provisional Authority to Operate) | bar: Year 4 (2030) 3 to Year 4 (2030) 4
TOTAL PROJECT COST:
Prepared by: Approved by:
Authorized Representative | Year 4 (2030) 1: Name of Official
Designation, Company | Year 4 (2030) 1: Designation, Company